## Sheet1
Sprint backlog
Project Name | Smart City
Project Manager | Lachlan Feeney
Start Date | 2017-10-02
End Date | 2017-10-23
Overall Progress
Backlog Item | Story Points | Status | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Time taken (hrs)
User Story #10 - Adding other admins | 4 | COMPLETE | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
User Story #16 - View City Information | 2 | COMPLETE | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
User Story #18 - View industry information | 2 | COMPLETE | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
User Story #23 - View hotel information - businessman | 2 | COMPLETE | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
User Story #40 - Change account | 4 | COMPLETE | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
User Story #47 - Update Account information | 4 | COMPLETE | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
User Story #14 - View Hotel list | 2 | COMPLETE | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
User Story #21 - View industry list | 2 | COMPLETE | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
User Story #26 - View hotel list | 2 | COMPLETE | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
User Story #30 - View Libraries list | 2 | COMPLETE | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
User Story #34 - View Colleges List | 2 | COMPLETE | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 3
User Story #15 - interact with hotel list | 2 | COMPLETE | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 3
User Story #17 - interact with city information | 2 | COMPLETE | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2
User Story #22 - Interact with industry list | 2 | COMPLETE | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 2
User Story #27 - Interact with hotel list - businessman | 2 | COMPLETE | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 2
User Story #31 - Interact with industry list | 2 | COMPLETE | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 4
User Story #50 - View City Map | 4 | COMPLETE | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
User Story #35 - Interact with hotel list - businessman | 2 | COMPLETE | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 3
Ideal Total |  |  | 41.8 | 39.6 | 37.4 | 35.2 | 33 | 30.8 | 28.6 | 26.4 | 24.2 | 22 | 19.8 | 17.6 | 15.4 | 13.2 | 11 | 8.8 | 6.6 | 4.4 | 2.2 | 0 | 44
Actual Total |  |  | 44 | 44 | 44 | 44 | 44 | 36 | 36 | 36 | 30 | 30 | 26 | 20 | 20 | 14 | 10 | 6 | 2 | 2 | 0 | 0 | 57
COMMENTS: - Hours taking slighly more than anticipated from sprint plan per task - needs to be factored into workload - Week one week 1 tutorial public holiday left team behind - need to catch up on missed time - Streamline similar tasks at once instead of one by one to speed progress up