## Sheet1
Sprint backlog
Project Name | Smart City
Project Manager | Lachlan Feeney
Start Date | 2017-08-14
End Date | 2017-10-23
Overall Progress
Backlog Item | Story Points | Responsible | Status | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20
User Story #48 | 4
Task: Design database structure
Task: Create database
Task: Verify story is complete
User Story #49 | 4
Task: Design database structure
Task: Create database
Task: Verify story is complete
User Story #1 | 2
Task: Create main page
Task: Test main page in specified browsers
Task: Verify story is complete
User Story #8 | 4
Task : Create add information page
Task: Write test cases
Task: Write code to add information to database
Task: Verify story is complete
User Story #2 | 4
Task: Create sign up page
Task: Write test cases
Task: Write code to send data submitted from sign up page to database
Task: Verify story is complete
User Story #3 | 2
Task: Write test cases
Task: Write code to add student account type to sign up page
Task: Verify story is complete
User Story #4 | 2
Task: Write test cases
Task: Write code to add tourist account type to sign up page
Task: Verify story is complete
User Story #5 | 2
Task: Write test cases
Task: Write code to add businessman account type to sign up page
Task: Verify story is complete
User Story #6 | 4
Task: Create login page
Task: Write test cases
Task: Write code to verify login details
Task: Create user's home page
Task: write code to respond to login attempt
Task: Verify story is complete
User Story #7 | 4
Task: Create admin login page
Task: Write test cases
Task: Write code to verify admin login details
Task: Create admin's home page
Task: write code to respond to login attempt
Task: Verify story is complete
Ideal Total |  |  |  | 30.4 | 28.8 | 27.2 | 25.6 | 24 | 22.4 | 20.8 | 19.2 | 17.6 | 16 | 14.4 | 12.8 | 11.2 | 9.6 | 8 | 6.4 | 4.8 | 3.2 | 1.6 | 0
Actual Total |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0