## Sheet1
Sprint backlog
Project Name | Smart City
Project Manager | Lachlan Feeney
Start Date | 2017-10-02
End Date | 2017-10-23
Overall Progress
Backlog Item | Story Points | Status | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20
User Story #10 - Adding other admins | 4 | COMPLETE | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Story #16 - View City Information | 2 | COMPLETE | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Story #18 - View industry information | 2 | COMPLETE | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Story #23 - View hotel information - businessman | 2 | COMPLETE | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Story #11 - Select city | 1 | COMPLETE | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Story #40 - Change account | 4 | COMPLETE | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Story #47 - Update Account information | 4 | COMPLETE | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Story #14 - View Hotel list | 2 | COMPLETE | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Story #21 - View industry list | 2 | COMPLETE | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Story #26 - View hotel list | 2 | COMPLETE | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Story #30 - View Libraries list | 2 | COMPLETE | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Story #34 - View Colleges List | 2 | COMPLETE | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
User Story #15 - interact with hotel list | 2 | COMPLETE | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
User Story #17 - interact with city information | 2 | COMPLETE | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
User Story #22 - Interact with industry list | 2 | COMPLETE | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
User Story #27 - Interact with hotel list - businessman | 2 | COMPLETE | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
User Story #31 - Interact with industry list | 2 | COMPLETE | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
User Story #35 - Interact with hotel list - businessman | 2 | COMPLETE | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
Ideal Total |  |  | 38.95 | 36.9 | 34.85 | 32.8 | 30.75 | 28.7 | 26.65 | 24.6 | 22.55 | 20.5 | 18.45 | 16.4 | 14.35 | 12.3 | 10.25 | 8.2 | 6.15 | 4.1 | 2.05 | 0
Actual Total |  |  | 41 | 41 | 41 | 41 | 41 | 37 | 37 | 37 | 31 | 31 | 26 | 20 | 20 | 14 | 10 | 6 | 2 | 2 | 0 | 0